## Note (hidden)
Note: This is the master template spreadsheet for BA Managed Services Weekly Status reports. It is set up to select data from IBM managed service statistics (as an example of real data). This is for testing only and must NOT be copied or given to anybody - must remain accessible by BA only on Sharepoint. This template is copied for each individual supplier and the passwords changed to access only the individual supplier's SLA data. This template should be copied for each new release of the spreadsheet so that the automated functionality is up-to-date. Any local data such as: Summary, Risks, Enhancements, Deliveries, CSIs, Actions will need to be copied across to the new copy of the latest template.

## Summary
Key highlights & lowlights
Highlights: NA Lowlights: NA Ongoing Activities: RMS applications upgrade , Ops dashboard new requirement, Datadog onboarding & Vulnerability Remediation activities are on going.
Key Incidents (Sev1, Sev2 or Business sensitive) this week
Resolution Date | System/Area | Incident Number | Details | Business Impact | Status | Root Cause & Resolution | Converted to Root Cause? (If yes, please provide the RC number)
None
Changes implemented this week
Implementation Date | System/Area | CR Number | Details | Business objective | Is this service improvement ? | Managed Service Partner Change Owner Y/N
2026-07-28 12:00 | OPDEFS (prd) | CHG0258672 | Database - Content Change | BAU change | No | N
2026-07-30 02:00 | RMS (prd) | CHG0258543 | Weekly BaseData updates for the RMS Instances | BAU change | No | N
Changes Planned
Implementation Date | System/Area | CR Number | Details | Business objective | Is this service improvement ? | Managed Service Partner Change Owner Y/N
2026-08-05 06:00 | RMS (prd) | CHG0259386 | Weekly BaseData updates for the RMS Instances | BAU change | No | N
2026-08-10 23:45 | RIBI (prd) | CHG0258654 | RiBi - Vulnerability remediation - Phase 2 | BAU change | No | N
2026-08-03 23:45 | RIBI (prd) | CHG0256747 | RiBi - Vulnerability remediation - Phase 1 | BAU change | No | N
Changes Failed this week
Implementation Date | System/Area | CR Number | Details | Business objective | First time implementation successful ? (yes/no) | Is this a service improvement?
None
Operational Health
No impact to operational health of any application during this period.

## SLA Breach Reasons (hidden)
Unusual circumstances
Working on unplanned work at the request of IAG
Excessive number of tickets
Reliance on other teams but ticket not in 'awaiting business' status
Incorrectly reported due to tool restrictions

## Dashboard
Summary SLA - KPI Dashboard ( Populated from 'Summary SLA Sheet')
| Incident |  |  | RFS
|  |  | Count | Week | Count
| P1 | Week 5 | 2 | Week 5 | 30
|  | Week 4 | 0 | Week 4 | 26
|  | Week 3 | 1 | Week 3 | 28
|  | Week 2 | 1 | Week 2 | 30
| P2 | Week 5 | 3
|  | Week 4 | 2
|  | Week 3 | 1
|  | Week 2 | 2
| P3 | Week 5 | 15
|  | Week 4 | 14
|  | Week 3 | 16
|  | Week 2 | 18
| P4 | Week 5 | 20
|  | Week 4 | 16
|  | Week 3 | 16
|  | Week 2 | 12

## Summary SLA
Service Metric | Ticket Type | Category | SLA | Target | Actual | Count of Incidents | Total Incidents | Actual Status
Time to Resolve | Incident | Severity 1 Incidents | Within 1 hour | 85% | 0% |  |  | GREEN | ONLY 100% Breach mark as 'RED' . All other breach mark it as 'Amber' . Mark the columnn in the colour as Text( Green as Green & Amber as Amber)
|  |  | Within 2 hours | 95% | 0% |  |  | GREEN
|  |  | Within 4 hours | 100% | 0% |  |  | GREEN
Time to Resolve | Incident | Severity 2 Incidents | Within 2 hours | 85% | 0% |  |  | GREEN
|  |  | Within 6 hours | 95% | 0% |  |  | GREEN
|  |  | Within 8 hours | 100% | 0% |  |  | GREEN
Time to Resolve | Incident | Severity 3 Incidents | Within 1 working day | 60% | 0% |  |  | AMBER
Time to Resolve | Incident |  | Within 5 working days | 100% | 0% |  |  | AMBER
Time to Resolve | Incident | Severity 4 Incidents | Within 10 working days | 80% | 0% |  |  | GREEN
Time to Resolve | Incident |  | Within 15 working days | 100% | 0% |  |  | GREEN
Time to Respond | Incident | Severity 1 Incidents | Within 15 minutes | 100% | 100% |  |  | GREEN
|  | Severity 2 Incidents | Within 30 minutes | 100% | 100% |  |  | GREEN
|  | Severity 3 Incidents | Within 2 business hours | 100% | 0% |  |  | RED
|  | Severity 4 Incidents | Within 3 business hours | 100% | 0% |  |  | RED
Service Metric | Ticket Type | Category | SLA | Target | Actual | Count | Total | Actual Status
Known Error Logging | Problem | High/High | Plan of action detailing options, dependencies, risks and timescales for fixing the problem to be available within 5 working days | 100%
Known Error Logging | Problem | All other priorities except High | Plan of action detailing options, dependencies, risks and timescales for fixing the problem to be available within 20 working days | 100%
Reoccuring Incident - Problem creation | Problem | All | Problem creation for reoccuring problems | 100%

## All_Ticket_Details
S.No | Op Co | Domain | Type | Reference Number | Queue Name | Priority | Title-Description | Status | Assigned to | Created date & time | Assigned date & time | Acknowledged date & time | Resolved date & time | Clock suspended Time | Clock resume Time | Impacted Application | P Ticket Ageing | Is SLA Applicable (For RFS) | Resolution Type | Root cause category | Duplicate Incident | RFS Category | Remarks | Planned IT Delivery | Planned Go Live | Current Status | ESG/EIM Owner | Incident Hours | Incident Total Age | Inc Current hours(FROM ASG) | Incident Current Age | Response SLA | Cumulative SLA | Cumulative days | Time Taken (in Hours) | Met Response SLA | Met Minimum Resolution SLA | Met Maximum Resolution SLA | Analysed Date

## Enhancement Tracker
Enhancement Bucket - 2025 -2026
Total Days | 50
Pending Approval | 0
In Progress | 0
Completed | 50
Remaining | None
Domain | Application | Enhancement Details | Benefits | Planned End date | Estimated Effort (pd) | Status | Comments | Received in Current week | Planned delivery in Current week
Airport Ops | Operational Dashboard | UI cleanup changes | We have identified multiple pages where UI cleanup is required. This will help correct the existing inconsistencies in the application. Post this cleanup, ops dashboard will display consistent data across all the affected pages ensuring users will be able to see accurate data. | 2025-11-24 | 4 | Completed
Airport Ops | Operational Dashboard | Entra Migration | Ops dashboard is planned to be migrated to Entra mode of authentication wherein users will be using a single sign on instead of multiple. This is prioritized by BA to enhance security and identity protection and to keep the organisation compliant to regulations. | 2026-04-13 | 10 | Completed
Airport Ops | Staff Admin | Business requirement – Weigand code tagged against the staff in TMS History table should be marked with an invalid date since these are currently not active/used by that staff | This would help the business to re-assign the code to different staff IDs to handle pass management effectively and will reduce the issues reported Weigand code assignment to new starters. | 2025-09-20 | 5 | Completed
Airport Ops | ATR | Application Enhancement - to create new automation script for housekeeping process of the clocking table to retain only 30days for data to increase database performance | This enhancement will implement Control-M Job through automation script for database housekeeping provides a structured and reliable approach to maintaining database health, ultimately supporting business operations more effectively. | 2026-03-31 | 10 | On hold | Ongoing project activities for migration
Airport Ops | ART | ART to Entra Migration | ART users Mod-Mellon for Authentication and this will be decommissioned by 31stMay2025. Ba cyber team have requested us to migrate ART to Entra which is the latest authentication used in IAG | 2025-10-31 | 15 | Completed
Airport Ops | RMS GGS | Atea is migrating their existing DC to a new DC. RMS GGS needs to be moved as part of this migration. | Atea is migrating their existing DC to a new DC. RMS GGS needs to be moved as part of this migration. ATEA will shut down the existing DC by end of March and hence the requirement is to migrate the RMS GGS environment to the new data center before the shutdown to ensure service continuity. | 2026-03-23 | 5 | Completed
Airport Ops | ART | ART application new release | New procedures and packages were created as part of new requirements which is to create the ability to store and view configurable historical data alongside snapshot views of resource figures in ART | 2026-05-08 | 5 | Completed
Airport Ops | LHR PCC | Migration of existing SharePoint 2013 workflow to Microsoft Powered modern Power Automate Flows. | • SharePoint 2013 workflows will be retired on 02 April 2026, making the current solution non‑functional. • Ensures long‑term stability, supportability, and compliance with Microsoft’s cloud roadmap. • Reduces complexity by eliminating REST‑based custom logic. • Provides better monitoring, error handling, and automation audit trails. | 2026-06-05 | 9 | Completed
Airport Ops | Operational Dashboard, ART,CJD | Helios Onboarding | Helios provides analysis and actionable insights through tools enabling to make data-driven decisions about software health and technical debt. Onboarding an application to Helios allows viewer to analyse metrics at every level for code health, unit test coverage and application security. | 2026-06-12 | 5 | Completed
Airport Ops | RMS suite of apps (RAMP,ACM,LGW,BAGGAGE,GTS,PSU,T3IB), Staff Admin, CJD, Operational Dashboard | Data Dog Onboarding | As part of IAG monitoring requirements, all SL1/SL2 applications must be onboarded to DataDog to ensure appropriate operational oversight and governance. Implementing DataDog monitoring will provide: • Real-time visibility into application performance and health • Early detection of issues to minimise business impact • Faster troubleshooting and reduced downtime • Centralised dashboards for improved transparency • Alignment with IAG monitoring and compliance standards • Actionable insights to support better decision-making | 2026-06-30 | 5 | In Progress

## Support Delivery Items
OpCo | Domain | Application | Delivery Item | Requested by (Delivery / Business/ Infrastructure/Service Trending) | Planned Start | Planned End | Actual End date | Status | Comments
BA | Airport Ops | JBS | JBS Decommissioning | Delivery | Decommission of phase 1 has been completed | Done |  | Decommission of phase 1 has been completed | Done
BA | Airport Ops | Transview | Transview decommissioning | Delivery | Got the Business approval to proceed with the decomm activities | Done |  | Got the Business approval to proceed with the decomm activities | Done
BA | Airport Ops | Brisk | Brisk decommissioning | Delivery | Started with the decomm activities | Done |  | Started with the decomm activities | Done
BA | Airport Ops | Figaro | Figaro On prem server decommissioning | Delivery | Figaro colo migration is in progress once it's completed we will proceed with On prem server decomm | Done |  | Figaro colo migration is in progress once it's completed we will proceed with On prem server decomm | Done
BA | Airport Ops | ATR | ATR Upgrade and cloud migration | Delivery | Completed | ATR application migration from on-prem to AWS hs been completed successfully. |  | Completed | ATR application migration from on-prem to AWS hs been completed successfully.
BA | Airport Ops | RMS & Other Apps | Control-M Upgrade | Delivery | Completed | Control M v9.0.0.500 migration cutover to the AWS for the Production Environment from On-Premises |  | Completed | Control M v9.0.0.500 migration cutover to the AWS for the Production Environment from On-Premises
BA | Airport Ops | Staff admin | ETL Upgrade and Cloud migration | Delivery | Completed | The current ETL platform is migrated and change is required to establish communication between the AWS ETL 10.5 servers and our application servers/database |  | Completed | The current ETL platform is migrated and change is required to establish communication between the AWS ETL 10.5 servers and our application servers/database
BA | Airport Ops | RMS | RMS upgrade and migration | Delivery | Completed | All RMS Applications have been migrated from on-prem to AWS . |  | Completed | All RMS Applications have been migrated from on-prem to AWS .
BA | Airport Ops | Staff Travel Airport | Staff Travel Airport decommission | Delivery | In Progress | working on decommission activities |  | In Progress | working on dev account decommission activities
BA | Airport Ops | Traka | Traka decommission | Delivery | In Progress | working on decommission activities |  | In Progress | working on AWS account decommission activities
BA | Airport Ops | RMS PSU | RMS PSU application decommission | Delivery | In Progress | working on decommission activities |  | In Progress | working on COSI feed disablement & NLV account decommission activities

## Risk & Issues
Impact | Area(s) of Impact | Probability | Mitigation | Owner | Action By Date | Status | Remarks
Impact to the application stability and causes slowness. The latest security patch will not be available. | Transview | Medium | Upgrade to latest Windows version(2016 or 2019) | Support Team | 2026-06-25 | "Risk has been registered. (KNOWN ERROR ARTICLE = KB0013546 v0.02, RISK Ref = Jira Ref - BDOEDP-377, PRB0054179)" | CJD has fixed it.
Brisk application used to be hosted in 2 datacentres – Cranebank and Boho. After March 2025, the Cranebank DC is moving out of support. Hence, the application needs to be hosted in only the Boho DC. | Brisk | Medium | Migrate to AWS | DC Exit Team | 2026-06-25 | Cyber Risk Form have been created | Done
Figaro application used to be hosted in 2 datacentres – Cranebank and Boho. After March 2025, the Cranebank DC is moving out of support. Hence, the application needs to be hosted in only the Boho DC. | Figaro | Medium | Migrate to AWS | DC Exit Team | 2026-09-25 | Cyber Risk Form have been created | Application have been migrated to colo
The Brisk application uses Apache log4j 1.2.13 version as the sole logging framework. There is a risk to continuing the use of Apache log4j 1.x due to several security and operational factors as its an end-of-life version with no official support or security patches. We will not be able to remove this dependency without impacting the application and upgrading the version would involve significant costs and efforts which is not a viable option. | Brisk | Medium | Migrate to AWS | DC Exit Team | 2026-06-25 | Cyber Risk Form have been created | Done
No support from vendor. The latest security patch will not be available and vulnerable to attack. | RMS GM, ACM, T3IB, GTS, RAMP,PSU,BL | Medium | Upgrade to latest RHEL version (7 or 8) | AMS/ GCS | TBC | Pipeline- Yet to start | RMS_RHEL6 server upgrade to higher version- POC to start shortly
No support from vendor. The latest security patch will not be available and vulnerable to attack. | GS Planning | Medium | Upgrade to latest RHEL version (7 or 8) | AMS/ GCS | TBC | Pipeline- Yet to start
No support from vendor. The latest security patch will not be available and vulnerable to attack. | RMS GM, ACM, T3IB, GTS, RAMP,PSU,LGW,BL | Medium | Enable only TLS V1.2 | AMS | TBC | In progress
No support from vendor. The latest security patch will not be available and vulnerable to attack. | ATR, RMS | Medium | Upgrade DB version to Oracle 12c or 19c | Project Team/ AMS | TBC | Completed | ATR- As part of upgrade, server moves to MY SQL SERVER
Minimal support from vendor since the application is in old version. | ATR | Medium | Upgrade to latest ATR version 8 | ATR project team/AMS | APR'26 | Completed | Upgrade work in progress and tentatively planned to go live in APR'26.

## OS Patching
Application Name | AWS Account name | AWS Account ID | Environment | Change details | Last/ Upcoming patching date | Status | Remarks
RMS GTS (prd) | ba-rms-gts-prd | 58264477828 | PRD | CHG0256043 | 7/28/2026 | Completed | NA
ATTENDANCE TIME REC VEIGHT (prd) | ba-attendance-time-rec-veigh-prd | 641241382097 | PRD | CHG0255658 | 7/27/2026 | Completed | NA
GS PLANNING(prd) | ba-AirportOps-gsplanning | 835530948614 | PRD | CHG0255898 | 7/21/2026 | Completed | NA
RMS LGW CUSTOMER SERVICE(prd) | ba-rms-lgw-customer-services-prd | 381492269129 | PRD | CHG0256731 | 7/22/2026 | Completed | NA
RMS PSU(prd) | ba-rms-psu-prd | 533266977564 | PRD | CHG0248372 | 7/22/2026 | Completed | NA
FIGARO(dev) | figaro-cola servers | 533267246670 | DEV | CHG0259351 | 2026-08-03 | Completed | NA
RMS RAMP TEAMWORKING (prd) | ba-rms-ramp-teamworking-prd | 992382737864 | PRD | CHG0256078 | 2026-08-06 | In-Progress | NA

## Vulnerability Remediation
|  |  |  | Before Patching |  |  |  | After Patching
AWS Account Name | Account ID | Application name | Env | Critical | High | Medium | Low | Critical | High | Medium | Low | Remediation action | Status
ba-oscs-prd | 241533157440 | OSCS | PRD | 0 | 10 | 0 | 2 |  |  |  |  | The vulnerability is related to the version and needs to be checked by the application support Team | High priority vulnerabilities has been remediated and low are not having fix available
ba-oscs-dev | 886436930590 | OSCS | DEV | 0 | 2 | 0 | 2 |  |  |  |  | The vulnerability is related to the version and needs to be checked by the application support Team | High priority vulnerabilities has been remediated and low are not having fix available
ba-oscs-uat | 783764617355 | OSCS | UAT | 0 | 4 | 0 | 2 |  |  |  |  | The vulnerability is related to the version and needs to be checked by the application support Team | High priority vulnerabilities has been remediated and low are not having fix available
ba-rms-t3-integrated-baggage-dev | 767397932450 | RMS T3IB | DEV | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-rms-t3-integrated-baggage-tst | 471112506428 | RMS T3IB | TST | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-rms-t3-integrated-baggage-trn | 471112852970 | RMS T3IB | TRN | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-rms-t3-integrated-baggage-uat | 637423228479 | RMS T3IB | UAT | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-rms-t3-integrated-baggage-prl | 730335284597 | RMS T3IB | PRL | 3 | 20 | 122 | 4 | 3 | 21 | 124 | 4 | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-rms-t3-integrated-baggage-prd | 730335333823 | RMS T3IB | PRD | 3 | 44 | 226 | 12 | 3 | 47 | 232 | 12 | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-attendance-time-recording-dev | 654654334334 | ATR | DEV | 1 | 24 | 23 | 0 |  |  |  |  | 1)Critical - Update to supported operation system 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel dnf update kernel-core dnf update python3-perf dnf update kernel-modules dnf update kernel-tools-libs dnf update kernel-tools dnf update libsoup 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-tools-libs dnf update kernel-modules dnf update python3-perf dnf update kernel-core dnf update kernel-tools dnf update kernel dnf update libmount dnf update util-linux dnf update libsmartcols dnf update libfdisk dnf update libblkid dnf update libuuid dnf update util-linux-user dnf update libuuid-devel dnf update brotli dnf update openssl-perl dnf update openssl dnf update openssl-libs | In Progress
ba-attendance-time-recording-stg | 767398079822 | ATR | STG | 0 | 0 | 0 | 0 |  |  |  |  | NA | In Progress
ba-attendance-time-recording-prd | 590183747819 | ATR | PRD | 2 | 99 | 72 | 4 |  |  |  |  | 1)Critical -Update to a supported operating system. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libtiff dnf update glib2 dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update sssd-krb5-common dnf update sssd-ad dnf update libipa_hbac dnf update sssd-common-pac dnf update sssd-proxy dnf update libsss_sudo dnf update sssd-polkit-rules dnf update libsss_idmap dnf update sssd-nfs-idmap dnf update python3-sss dnf update sssd-ldap dnf update sssd-krb5 dnf update sssd-winbind-idmap dnf update libsss_nss_idmap dnf update sssd-tools dnf update libsss_certmap dnf update libsss_autofs dnf update sssd-dbus dnf update sssd dnf update libsss_simpleifp dnf update sssd-client dnf update python3-sssdconfig dnf update sssd-ipa dnf update sssd-kcm dnf update sssd-common dnf update libsoup dnf update bind-license dnf update bind-libs dnf update bind-utils dnf update bind-export-libs dnf update python3-bind dnf update bind-libs-lite 3)Medium - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update python3.12-libs dnf update python3.11-libs dnf update platform-python dnf update python3.12 dnf update python3.11 dnf update python3-libs dnf update python3-urllib3 dnf update libsoup dnf update libcurl dnf update curl dnf update libpq dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update openssl-perl dnf update openssl-libs dnf update openssl dnf update openssh dnf update openssh-clients dnf update openssh-server dnf update binutils dnf update expat-devel dnf update expat dnf update libpng-devel dnf update java-1.8.0-openjdk-headless dnf update java-17-openjdk dnf update libpng dnf update java-1.8.0-openjdk-devel dnf update java-1.8.0-openjdk dnf update java-17-openjdk-headless dnf update libblkid dnf update util-linux dnf update libsmartcols dnf update libmount dnf update libfdisk dnf update util-linux-user dnf update libuuid-devel dnf update libuuid dnf update brotli dnf update cups-client dnf update cups-libs dnf update vim-enhanced dnf update vim-filesystem dnf update vim-minimal dnf update vim-common dnf update gnutls dnf update gnutls-utils dnf update gnutls-dane dnf update expat-devel dnf update expat 4)Low - Upgrade your installed software packages to the proposed fixed in version and release. dnf update kernel-modules dnf update kernel-core dnf update kernel dnf update libsoup dnf update python3.12-libs dnf update python3.12 | In Progress
ba-nlv-airportops-art | 725662711609 | ART | NLV | 2 | 0 | 0 | 0 |  |  |  |  | Critical - Update to a supported operating system. | In Progress
ba-prd-airportops-art | 965893310331 | ART | PRD | 4 | 0 | 0 | 0 |  |  |  |  | Critical - Update to a supported operating system. | In Progress
ba-uat-airportops-art | 227297286911 | ART | UAT | 2 | 0 | 0 | 0 |  |  |  |  | Critical - Update to a supported operating system. | In Progress
ba-rms-lgw-customer-services-dev | 211125789846 | LGW | dev | 1 | 11 | 27 | 2 | 1 | 11 | 27 | 2 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | Completed
ba-rms-lgw-customer-services-prd | 381492269129 | LGW | prd | 3 | 33 | 152 | 4 | 3 | 33 | 152 | 4 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | Completed
ba-rms-lgw-customer-services-prl | 905418111468 | LGW | PRL | 4 | 27 | 132 | 3 | 4 | 27 | 150 | 3 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | Completed
ba-rms-lgw-customer-services-uat | 533267357364 | LGW | uat | 1 | 11 | 28 | 2 | 1 | 11 | 28 | 2 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | Completed
ba-rms-baggage-dev | 339712711929 | BAGGAGE | DEV | 1 | 14 | 45 | 2 | 1 | 14 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-baggage-tst | 637423195592 | BAGGAGE | TST | 1 | 13 | 45 | 2 | 1 | 13 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-baggage-trn | 590183819048 | BAGGAGE | TRN | 1 | 13 | 46 | 2 | 1 | 13 | 46 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-baggage-uat | 533267254369 | BAGGAGE | UAT | 1 | 13 | 45 | 2 | 1 | 13 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-baggage-prelive-prl | 851725176206 | BAGGAGE | PRL | 3 | 30 | 134 | 8 | 3 | 30 | 134 | 6 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-baggage-prd | 339712973238 | BAGGAGE | PRD | 3 | 56 | 200 | 14 | 3 | 56 | 200 | 14 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-aircraft-movements-p-prd | 533267057136 | ACM | PRD | 3 | 29 | 30 | 6 | 3 | 54 | 242 | 14 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-aircraft-movements-p-prl | 654654410889 | ACM | PRL | 3 | 17 | 30 | 2 | 3 | 16 | 79 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-aircraft-movements-d-dev | 767397922332 | ACM | DEV | 1 | 13 | 30 | 2 | 1 | 18 | 62 | 3 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-aircraft-movements-t-tst | 590183807077 | ACM | TST | 1 | 13 | 30 | 2 | 1 | 13 | 43 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-aircraft-movements-t-trn | 851725228901 | ACM | TRN | 1 | 13 | 30 | 2 | 1 | 13 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-aircraft-movements-u-uat | 590183949240 | ACM | UAT | 1 | 13 | 30 | 2 | 1 | 13 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-psu-dev | 992382720474 | PSU | DEV | 1 | 17 | 32 | 4 | 1 | 17 | 32 | 4 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-psu-tst | 851725336212 | PSU | TST | 1 | 11 | 28 | 2 | 1 | 11 | 28 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-psu-trn | 851725163912 | PSU | TRN | 1 | 11 | 28 | 2 | 1 | 11 | 28 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-psu-uat | 533267254369 | PSU | UAT | 1 | 17 | 32 | 4 | 1 | 17 | 32 | 4 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-psu-prelive-prl | 730335585963 | PSU | PRL | 3 | 22 | 89 | 6 | 3 | 27 | 93 | 6 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-rms-psu-prd | 533266977564 | PSU | PRD | 3 | 40 | 139 | 10 | 3 | 40 | 145 | 10 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-prd-airportops-watchlist | 368576248406 | Watchlist | PRD | 8 | 37 | 15 | 5 |  |  |  |  | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-uat-airportops-watchlist | 221579245067 | Watchlist | UAT | 6 | 389 | 290 | 27 |  |  |  |  | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-operational-dashboard-pr-prd | 992382395097 | Operational Dashboard | PRD | 2 | 140 | 128 | 4 | 2 | 56 | 48 | 4 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-operational-dashboard-pr-prl | 851725501381 | Operational Dashboard | PRL | 2 | 28 | 24 | 4 | 2 | 56 | 48 | 4 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-operational-dashboard-ua-uat | 637423444507 | Operational Dashboard | UAT | 1 | 14 | 14 | 2 | 1 | 28 | 24 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-operational-dashboard-ts-tst | 471112663701 | Operational Dashboard | TST | 1 | 14 | 14 | 2 | 1 | 28 | 24 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-operational-dashboard-de-dev | 471112620804 | Operational Dashboard | DEV | 24 | 905 | 2507 | 64 | 34 | 1033 | 2875 | 77 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-prd-it-trakat5t3loc | 593665234721 | Traka | PRD | 0 | 3 | 5 | 0 |  |  |  |  | NA | In Progress
ba-nlv-it-trakat5t3loc | 867328132590 | Traka | NLV | 0 | 3 | 2 | 0 |  |  |  |  | NA | In Progress
ba-customer-journey-dashboar-prd | 730335673794 | CJD | PRD | 2 | 41 | 72 | 33 |  |  |  |  | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-opstransfersdash-dev | 280970835228 | CJD | DEV | 0 | 6 | 12 | 6 |  |  |  |  | NA | In Progress
ba-opstransfersdash-tst | 402757385722 | CJD | TST | 1 | 13 | 32 | 5 |  |  |  |  | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-opstransfersdash-uat | 637423381944 | CJD | UAT | 7 | 86 | 43 | 57 |  |  |  |  | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 4)Low -Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-opstransfersdash-nft-prl | 211125753162 | CJD | PRL | 0 | 5 | 9 | 4 |  |  |  |  | 1) High - Upgrade your installed software packages to the proposed fixed in version and release. 2) Medium - Upgrade your installed software packages to the proposed fixed in version and release. 3)Low -Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-ramp-teamworking-prd | 992382737864 | RAMP | PRD | 3 | 21 | 124 | 4 | 3 | 23 | 127 | 4 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-ramp-teamworking-pre-prl | 471112503917 | RAMP | PRL | 4 | 25 | 82 | 2 | 4 | 25 | 83 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-ramp-teamworking-dev | 211125363252 | RAMP | DEV | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-ramp-teamworking-trn | 975050219494 | RAMP | TRN | 1 | 11 | 28 | 2 | 1 | 11 | 28 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-ramp-teamworking-tst | 975050282396 | RAMP | TST | 1 | 13 | 45 | 2 | 1 | 13 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-ramp-teamworking-uat | 992382785195 | RAMP | UAT | 1 | 13 | 45 | 2 | 1 | 13 | 45 | 2 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-rms-gts-dev | 975050012928 | GTS | DEV | 1 | 13 | 45 | 2 | 1 | 13 | 45 | 2 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | In Progress
ba-rms-gts-tst | 975050351542 | GTS | TST | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | In Progress
ba-rms-gts-trn | 905418119199 | GTS | TRN | 1 | 4 | 35 | 0 | 1 | 4 | 35 | 0 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | In Progress
ba-rms-gts-uat | 381492173848 | GTS | UAT | 1 | 4 | 35 | 0 | 1 | 9 | 52 | 1 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | In Progress
ba-rms-gts-prelive-prl | 851725329582 | GTS | PRL | 3 | 13 | 73 | 0 | 3 | 12 | 77 | 0 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | In Progress
ba-rms-gts-prd | 58264477828 | GTS | PRD | 3 | 61 | 247 | 14 | 3 | 56 | 242 | 14 | 1)Medium - Upgrade your installed software packages to the proposed fixed in version and release. 2)High - Upgrade your installed software packages to the proposed fixed in version and release. 2)Critical - Update to a supported operating system. | In Progress
ba-nlv-airportops-gsplanning | 449841127896 | GS Planning | NLV | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-prd-airportops-gsplanning | 835530948614 | GS Planning | PRD | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-staff-admin-dev | 730335250746 | Staff Admin | DEV | 0 | 250 | 450 | 200 | 0 | 250 | 450 | 200 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-staff-admin-prd | 471112757515 | Staff Admin | PRD | 2 | 102 | 307 | 107 | 2 | 450 | 650 | 256 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-staff-admin-prl | 381492094098 | Staff Admin | PRL | 0 | 113 | 303 | 172 | 0 | 307 | 850 | 356 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-staff-admin-uat | 471112512057 | Staff Admin | UAT | 1 | 27 | 71 | 43 | 1 | 67 | 179 | 70 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
iagc-alerts-prd | 730335654157 | Alerts | PRD | 0 | 690 | 808 | 52 | 0 | 982 | 1231 | 88 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
iagc-alerts-prelive-prl | 306612389453 | Alerts | PRD | 0 | 42 | 73 | 21 | 0 | 47 | 73 | 21 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
iagc-alerts-uat | 515851320393 | Alerts | PRD | 0 | 30 | 65 | 18 | 0 | 38 | 85 | 20 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
iagc-alerts-dev | 938106486237 | Alerts | PRD | 0 | 128 | 139 | 23 | 0 | 58 | 119 | 23 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | Completed
ba-ribi-dev | 535002885708 | RiBi | DEV | 24 | 243 | 405 | 65 | 24 | 243 | 405 | 65 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-ribi-prl | 961341554932 . | RiBi | PRL | 16 | 163 | 83 | 41 | 16 | 163 | 83 | 41 | l | In Progress
ba-ribi-uat | 202533526794 . | RiBi | UAT | 18 | 182 | 279 | 44 | 18 | 182 | 279 | 44 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress
ba-ribi-tst | 796973518145 | RiBi | TST | 18 | 182 | 309 | 50 | 18 | 182 | 309 | 50 | 1) Critical - Update to a supported operating system. 2) High - Upgrade your installed software packages to the proposed fixed in version and release. 3) Medium - Upgrade your installed software packages to the proposed fixed in version and release. | In Progress

## Datadog-Onboarding Tracker
Application name | Onboarding form | Get YAML File via mail | Integration and Datadog installation - GCS Team | Alert Creation in DOT platform | Dashboard creation in DOT platform | Status
ba-attendance-time-recording-prd | NA - To be completed by Project team | NA - To be completed by Project team | NA - To be completed by Project team | NA - To be completed by Project team | NA - To be completed by Project team
ba-operational-dashboard-pr-prd | Completed by BA AO | Yes | Integration is done AWS Integration issue - Checking with GCS Team (Will be prioritised after RMS onboarding) | 5 alerts have been created (CPU utilization ,Swap , Disk Space, /webserver disk usage,Telegraf Agent Heartbeat Monitor )
ba-rms-aircraft-movements-p-prd | Completed by BA AO | Yes | Integration completed-CHG0250247 | Not started
ba-rms-baggage-prd | Completed by BA AO | Yes | Reintegration is pending with GCS (Plannned for next week) | Not started
ba-rms-gts-prd | Completed by BA AO | Yes | Integration completed-CHG0251316 | Not started
ba-rms-lgw-customer-services-prd | Completed by BA AO | Yes | Integration completed-CHG0251497 | 3 alerts created(CPU, Disk space,Status checking failed )
ba-rms-psu-prd | Completed by BA AO | Yes | Integration completed-CHG0250248 | Not started
ba-rms-ramp-teamworking-prd | Completed by BA AO | Yes | Reintegration is pending with GCS (Plannned for next week) | Not started
ba-rms-t3-integrated-baggage-prd | Completed by BA AO | Yes | Integration completed-CHG0251498 | Not started
ba-staff-admin-prd | Completed by BA AO | Yes | Integration is done AWS Integration issue - Checking with GCS Team (Will be prioritised after RMS onboarding) | 8 alerts have been created (CPU utilization ,Swap , Disk Space, /webserver disk usage,Telegraf Agent Heartbeat Monitor,/root disk_usage,INSTANCE StatusCheckFailed, /chronyd/procstat_lookup_pid_count/ )
ba-staff-travel-airport-prd | NA - to be decommed | NA - to be decommed | NA - to be decommed | NA - to be decommed | NA - to be decommed
ba-customer-journey-dashboar-prd | ELS Signoff Pending |  | Awaiting for Signoff confirmation from GCS team
ba-ribi-prd | Completed by BA AO | Yes | REQ1170220 - Onhold by GCS team as they donot support 2942 instances

## Action Items
S.No | Activity | Status
1 | Closure of Brock Problem ticket | Completed
2 | Creation of Problem ticket for CJD BES alerts tickets | Completed
3 | RIBI Problem ticket - RiBi requests not auto-cancelling when pax boards | Completed
4 | RIBI Problem ticket - IAPP Selectee issue | Implementation completed
5 | Reason for LV service collector stopped in Loadview application | As checked we found that due to pacthing activity the service was stopped
6 | Problem ticket creation for Brock BSM outage | Completed

## SLA Definition
Service Metric | Ticket Type | Category | SLA | Target
Time to Respond | Incident | Severity 1 Incidents | Within 15 minutes | 100%
Time to Respond | Incident | Severity 2 Incidents | Within 30 minutes | 100%
Time to Respond | Incident | Severity 3 Incidents | Within 2 business hours | 100%
Time to Respond | Incident | Severity 4 Incidents | Within 3 business hours | 100%
Time to Resolve | Incident | Severity 1 Incidents | Within 1 hour | 85%
Time to Resolve | Incident | Severity 1 Incidents | Within 1 business hour where call outs NOT applicable | 85%
Time to Resolve | Incident | Severity 1 Incidents | Within 2 hours | 95%
Time to Resolve | Incident | Severity 1 Incidents | Within 2 business hour where call outs NOT applicable | 95%
Time to Resolve | Incident | Severity 1 Incidents | Within 4 hours | 100%
Time to Resolve | Incident | Severity 1 Incidents | Within 4 business hour where call outs NOT applicable | 100%
Time to Resolve | Incident | Severity 2 Incidents | Within 2 hours | 85%
Time to Resolve | Incident | Severity 2 Incidents | Within 2 business hour where call outs NOT applicable | 85%
Time to Resolve | Incident | Severity 2 Incidents | Within 6 hours | 95%
Time to Resolve | Incident | Severity 2 Incidents | Within 6 business hour where call outs NOT applicable | 95%
Time to Resolve | Incident | Severity 2 Incidents | Within 8 hours | 100%
Time to Resolve | Incident | Severity 2 Incidents | Within 8 business hour where call outs NOT applicable | 100%
Time to Resolve | Incident | Severity 3 Incidents | Within 1 day where call outs applicable | 60%
Time to Resolve | Incident | Severity 3 Incidents | Within 1 working day | 60%
Time to Resolve | Incident | Severity 3 Incidents | Within 5 days where call outs applicable | 100%
Time to Resolve | Incident | Severity 3 Incidents | Within 5 working days | 100%
Time to Resolve | Incident | Severity 4 Incidents | Within 10 working days | 80%
Time to Resolve | Incident | Severity 4 Incidents | Within 15 working days | 100%
Service Metric | Ticket Type | Category | SLA | Target
Time to Owner Assignment | Problem | All | Within 1 business day | 100%
Root Cause Analysis | Problem | High | Regular updates are provided on Root cause analysis (Problem) to the customer on closing a major incident OR a problem record being raised every 7 days | 100%
Root Cause Analysis | Problem | Medium | Regular updates are provided on Root cause analysis (Problem) to the customer on closing a major incident OR a problem record being raised every 14 days | 100%
Root Cause Analysis | Problem | Low | Regular updates are provided on Root cause analysis (Problem) to the customer on closing a major incident OR a problem record being raised every 21 days | 100%
Known Error Logging | Problem | High | Plan of action detailing options, dependencies, risks and timescales for fixing the problem to be available within 5 working days | 100%
Known Error Logging | Problem | Medium | Known Error status reviewed and updated every 30 days | 100%
Known Error Logging | Problem | All other priorities except High | Plan of action detailing options, dependencies, risks and timescales for fixing the problem to be available within 20 working days | 100%

## Incident SLA Breaches
Application Name | Incident ID | Seriousness | Assigned Date | Ackownledge Date | Resolved Date | SLA_DESCRIPTION ( Breach Description) | Waiver Y/N | Reason for Waiver | Comments | Remarks
None

## Problem Tickets Breaches
Application | Problem Reference | Problem Description/Summary | Date Logged | Date Plan Available | Resolved Date | Quarter | Severity | KPI Metric Breached | Reason | Action / Learning / Improvement | Owner | Due Date | IAG Service Lead Comments
None

## Failed Changes Tickets
Planned Implementation Date | Actual Implementation Date | Quarter | System/Area | Change Type | CR Number | Details | Business objective | Change successful Y/N | Reason for failed change | KPI Breach Waivered Y/N | Reson for Waiver from KPI calculation | Action / Learning / Improvement | Owner | Due Date | IAG Service Lead Comments
None

## Pivot Tables (hidden)
Count of RAG | Column Labels |  | Count of V_INCIDENT_ID |  |  | V_STATUS | [10 empty] | Count of V_INCIDENT_ID |  |  | V_STATUS
Row Labels | GREEN | Grand Total | V_ANALYSIS_SVD | V_ANALYSIS_FROM_DATE | V_TICKET_TYPE | 1 ON-QUEUE*OPENED-PREVIOUSLY*STILL-OPEN | 1 ON-QUEUE*OPENED-PREVIOUSLY*STILL-OPEN*TOUCHED | 2 ON-QUEUE*OPENED-PREVIOUSLY*CLOSED-THIS-PERIOD | 2 ON-QUEUE*OPENED-PREVIOUSLY*CLOSED-THIS-PERIOD*TOUCHED | 3 ON-QUEUE*OPENED-THIS-PERIOD*CLOSED-THIS-PERIOD*TOUCHED | 4 ON-QUEUE*OPENED-THIS-PERIOD*STILL-OPEN | 4 ON-QUEUE*OPENED-THIS-PERIOD*STILL-OPEN*TOUCHED | 5 OFF QUEUE*OPENED-PREVIOUSLY*STILL-OPEN*TOUCHED | 7 OFF QUEUE*OPENED-THIS-PERIOD*STILL-OPEN*TOUCHED | 8 OFF QUEUE*OPENED-THIS-PERIOD*CLOSED-THIS-PERIOD*TOUCHED | Grand Total | V_ANALYSIS_SVD | V_ANALYSIS_FROM_DATE | V_TICKET_TYPE | 1 - TOUCHED THIS WEEK | 2 - OPENED THIS WEEK | 3 - CLOSED THIS WEEK | 3a - CLOSED THIS WEEK - US | 3b - CLOSED THIS WEEK - OTHER | Grand Total
APMAPEX |  |  | APMAPEX | 2019-04-01 | INCIDENT |  |  |  |  | 1 |  |  | 1 | 2 |  | 4 | APMAPEX | 2019-04-01 | INCIDENT | 4 | 3 | 1 | 1 |  | 9
2019-04-01 |  |  |  |  | REQUEST | 3 | 1 |  | 1 | 2 |  | 2 |  | 1 |  | 10 |  |  | REQUEST | 7 | 5 | 3 | 2 | 1 | 18
1-Time to Respond: Sev 4 - within 3 hours, 100% | 1 | 1 |  | 01/04/2019 Total |  | 3 | 1 |  | 1 | 3 |  | 2 | 1 | 3 |  | 14 |  | 01/04/2019 Total |  | 11 | 8 | 4 | 3 | 1 | 27
3-Time to Resolve: Sev 4 - within 10 business day, 80% | 1 | 1 |  | 2019-04-08 | INCIDENT |  |  | 1 |  | 1 | 2 |  |  | 1 | 1 | 6 |  | 2019-04-08 | INCIDENT | 3 | 5 | 3 | 1 | 2 | 14
4-Time to Resolve: Sev 4 - within 15 business days, 100% | 1 | 1 |  |  | REQUEST | 2 | 3 | 1 | 1 |  |  | 2 | 1 |  |  | 10 |  |  | REQUEST | 7 | 2 | 2 | 1 | 1 | 13
2019-04-08 |  |  |  | 08/04/2019 Total |  | 2 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 16 |  | 08/04/2019 Total |  | 10 | 7 | 5 | 2 | 3 | 27
1-Time to Respond: Sev 3 - within 2 hours, 100% | 1 | 1 | APMAPEX Total |  |  | 5 | 4 | 2 | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 30 | APMAPEX Total |  |  | 21 | 15 | 9 | 5 | 4 | 54
2-Time to Resolve: Sev 3 - within 1 business day, 60% | 1 | 1 | Grand Total |  |  | 5 | 4 | 2 | 2 | 4 | 2 | 4 | 2 | 4 | 1 | 30 | Grand Total |  |  | 21 | 15 | 9 | 5 | 4 | 54
3-Time to Resolve: Sev 3 - within 5 business days, 100% | 1 | 1
Grand Total | 6 | 6